## Sheet1
System | Date | RCA | Resolution
Sandbox | 2022-08-10 | license expiration of a sub component in Kubernetes | applied permanent license
Sandbox | 2022-09-16 | The service restarts is overloaded, and during the restart the service pointers have got changed | Restarted few service and it resolved the issue
Dev | 2022-09-01 | Modeller app is not working for DI ,Modeller application is showing in starting status | Cloud Infrastructure team resolved the issue in Kubernetes